## Total Summary Chart
Summary Details -
% Testing completed | 66.0714
% Testing remained | 33.9286
Total Number of Scenarioes | 280
Total Scenarios Remaining | 17
Total No of Scenarios passed | 185
Total No of Scenarios failed | 0
% Passed | 66.0714
% Failed | 0

## MM-AL Integration Test
Test Plan AL Integration Test MM
Summary Details -
| % Testing completed | 0
| % Testing remained | 100
| Total Number of Scenarioes | 17
| Total No of Scenrioes passed | 0
| Total No of Scenrioes failed | 0
| % Passed | 0
| % Failed | 0
Scenarioes List -
S.NO. | Functions List | Status | Remarks
1 | CPP - PrintMode: Dapextract in AL (Auto Archive: true) + showQuote: HTMLPrint. Create CPP policy. Attach documents on it on documents tab and submit it. Verify after successful submit it does not show archive button below pdf container. Make it cycle run (Host + dap) and upload feeds in AL and access the policy in inquiry after successful archive. Open policy documents in inquiry, it navigates to MM logged in with respect to that perticular policy only. Check Policy documents Tab should contain one document. Open it and verify it opens successfully. Click on Multi-Media Tab and verify both the attached forms are present over here. Try to open them and verify they opened successfully. Close this MM window. Comes to History tab in inquiry. click on New Business link. verify it again brings back to the same MM window logged in with Perticular policy. Verify all the documents and forms are present. Now open Agent Inbox from tools, from left frame. It opens MM auto logged in as AL Agent. Search policy documents tab for the policy submitted. verify it shows the document on policy document tab for that policy. Verify multi-media tab as well and search the same policy there as well and check forms attached to the policy are present over there.
2 | BOP - PrintMode: Dapextract in AL (Auto Archive: true) + showQuote: HTMLPrint. Create BOP policy. Attach documents on it on documents tab and submit it. Verify after successful submit it does not show archive button below pdf container. Make it cycle run (Host + dap) and upload feeds in AL and access the policy in inquiry after successful archive. Open policy documents in inquiry, it navigates to MM logged in with respect to that perticular policy only. Check Policy documents Tab should contain one document. Open it and verify it opens successfully. Click on Multi-Media Tab and verify both the attached forms are present over here. Try to open them and verify they opened successfully. Close this MM window. Comes to History tab in inquiry. click on New Business link. verify it again brings back to the same MM window logged in with Perticular policy. Verify all the documents and forms are present. Now open Agent Inbox from tools, from left frame. It opens MM auto logged in as AL Agent. Search policy documents tab for the policy submitted. verify it shows the document on policy document tab for that policy. Verify multi-media tab as well and search the same policy there as well and check forms attached to the policy are present over there.
3 | DF - PrintMode: Dapextract in AL (Auto Archive: true) + showQuote: HTMLPrint. Create DF policy. Attach documents on it on documents tab and submit it. Verify after successful submit it does not show archive button below pdf container. Make it cycle run (Host + dap) and upload feeds in AL and access the policy in inquiry after successful archive. Open policy documents in inquiry, it navigates to MM logged in with respect to that perticular policy only. Check Policy documents Tab should contain one document. Open it and verify it opens successfully. Click on Multi-Media Tab and verify both the attached forms are present over here. Try to open them and verify they opened successfully. Close this MM window. Comes to History tab in inquiry. click on New Business link. verify it again brings back to the same MM window logged in with Perticular policy. Verify all the documents and forms are present. Now open Agent Inbox from tools, from left frame. It opens MM auto logged in as AL Agent. Search policy documents tab for the policy submitted. verify it shows the document on policy document tab for that policy. Verify multi-media tab as well and search the same policy there as well and check forms attached to the policy are present over there.
4 | HO - PrintMode: Dapextract in AL (Auto Archive: true) + showQuote: HTMLPrint. Create HO policy. Attach documents on it on documents tab and submit it. Verify after successful submit it does not show archive button below pdf container. Make it cycle run (Host + dap) and upload feeds in AL and access the policy in inquiry after successful archive. Open policy documents in inquiry, it navigates to MM logged in with respect to that perticular policy only. Check Policy documents Tab should contain one document. Open it and verify it opens successfully. Click on Multi-Media Tab and verify both the attached forms are present over here. Try to open them and verify they opened successfully. Close this MM window. Comes to History tab in inquiry. click on New Business link. verify it again brings back to the same MM window logged in with Perticular policy. Verify all the documents and forms are present. Now open Agent Inbox from tools, from left frame. It opens MM auto logged in as AL Agent. Search policy documents tab for the policy submitted. verify it shows the document on policy document tab for that policy. Verify multi-media tab as well and search the same policy there as well and check forms attached to the policy are present over there.
5 | WC - PrintMode: Dapextract in AL (Auto Archive: true) + showQuote: HTMLPrint. Create WC policy. Attach documents on it on documents tab and submit it. Verify after successful submit it does not show archive button below pdf container. Make it cycle run (Host + dap) and upload feeds in AL and access the policy in inquiry after successful archive. Open policy documents in inquiry, it navigates to MM logged in with respect to that perticular policy only. Check Policy documents Tab should contain one document. Open it and verify it opens successfully. Click on Multi-Media Tab and verify both the attached forms are present over here. Try to open them and verify they opened successfully. Close this MM window. Comes to History tab in inquiry. click on New Business link. verify it again brings back to the same MM window logged in with Perticular policy. Verify all the documents and forms are present. Now open Agent Inbox from tools, from left frame. It opens MM auto logged in as AL Agent. Search policy documents tab for the policy submitted. verify it shows the document on policy document tab for that policy. Verify multi-media tab as well and search the same policy there as well and check forms attached to the policy are present over there.
6 | PA - PrintMode: Dapextract in AL (Auto Archive: true) + showQuote: HTMLPrint. Create PA policy. Attach documents on it on documents tab and submit it. Verify after successful submit it does not show archive button below pdf container. Make it cycle run (Host + dap) and upload feeds in AL and access the policy in inquiry after successful archive. Open policy documents in inquiry, it navigates to MM logged in with respect to that perticular policy only. Check Policy documents Tab should contain one document. Open it and verify it opens successfully. Click on Multi-Media Tab and verify both the attached forms are present over here. Try to open them and verify they opened successfully. Close this MM window. Comes to History tab in inquiry. click on New Business link. verify it again brings back to the same MM window logged in with Perticular policy. Verify all the documents and forms are present. Now open Agent Inbox from tools, from left frame. It opens MM auto logged in as AL Agent. Search policy documents tab for the policy submitted. verify it shows the document on policy document tab for that policy. Verify multi-media tab as well and search the same policy there as well and check forms attached to the policy are present over there.
7 | MCA - PrintMode: Dapextract in AL (Auto Archive: true) + showQuote: HTMLPrint. Create MCA policy. Attach documents on it on documents tab and submit it. Verify after successful submit it does not show archive button below pdf container. Make it cycle run (Host + dap) and upload feeds in AL and access the policy in inquiry after successful archive. Open policy documents in inquiry, it navigates to MM logged in with respect to that perticular policy only. Check Policy documents Tab should contain one document. Open it and verify it opens successfully. Click on Multi-Media Tab and verify both the attached forms are present over here. Try to open them and verify they opened successfully. Close this MM window. Comes to History tab in inquiry. click on New Business link. verify it again brings back to the same MM window logged in with Perticular policy. Verify all the documents and forms are present. Now open Agent Inbox from tools, from left frame. It opens MM auto logged in as AL Agent. Search policy documents tab for the policy submitted. verify it shows the document on policy document tab for that policy. Verify multi-media tab as well and search the same policy there as well and check forms attached to the policy are present over there.
8 | WC - PrintMode: DapExtract in AL (Auto Archive: false) + showQuote: HTMLPrint. Create WC policy. Attach documents on it on documents tab and submit it. Verify after successful submit it shows archive button below pdf container. Click on it. verify it shows policy document is archived. Make it cycle run (Host + dap) and upload feeds in AL and access the policy in inquiry after successful archive. Open policy documents in inquiry, it navigates to MM logged in with respect to that perticular policy only. Check Policy documents Tab should contain one document. Open it and verify it opens successfully. Click on Multi-Media Tab and verify both the attached forms are present over here. Try to open them and verify they opened successfully. Close this MM window. Comes to History tab in inquiry. click on New Business link. verify it again brings back to the same MM window logged in with Perticular policy. Verify all the documents and forms are present. Now open Agent Inbox from tools, from left frame. It opens MM auto logged in as AL Agent. Search policy documents tab for the policy submitted. verify it shows the document on policy document tab for that policy. Verify multi-media tab as well and search the same policy there as well and check forms attached to the policy are present over there.
9 | PA - PrintMode: DapExtract in AL (Auto Archive: false) + showQuote: HTMLPrint. Create PA policy. Attach documents on it on documents tab and submit it. Verify after successful submit it shows archive button below pdf container. Click on it. verify it shows policy document is archived. Make it cycle run (Host + dap) and upload feeds in AL and access the policy in inquiry after successful archive. Open policy documents in inquiry, it navigates to MM logged in with respect to that perticular policy only. Check Policy documents Tab should contain one document. Open it and verify it opens successfully. Click on Multi-Media Tab and verify both the attached forms are present over here. Try to open them and verify they opened successfully. Close this MM window. Comes to History tab in inquiry. click on New Business link. verify it again brings back to the same MM window logged in with Perticular policy. Verify all the documents and forms are present. Now open Agent Inbox from tools, from left frame. It opens MM auto logged in as AL Agent. Search policy documents tab for the policy submitted. verify it shows the document on policy document tab for that policy. Verify multi-media tab as well and search the same policy there as well and check forms attached to the policy are present over there.
10 | HO - PrintMode: DapExtract in AL (Auto Archive: false) + showQuote: HTMLPrint. Create HO policy. Attach documents on it on documents tab and submit it. Verify after successful submit it shows archive button below pdf container. Click on it. verify it shows policy document is archived. Make it cycle run (Host + dap) and upload feeds in AL and access the policy in inquiry after successful archive. Open policy documents in inquiry, it navigates to MM logged in with respect to that perticular policy only. Check Policy documents Tab should contain one document. Open it and verify it opens successfully. Click on Multi-Media Tab and verify both the attached forms are present over here. Try to open them and verify they opened successfully. Close this MM window. Comes to History tab in inquiry. click on New Business link. verify it again brings back to the same MM window logged in with Perticular policy. Verify all the documents and forms are present. Now open Agent Inbox from tools, from left frame. It opens MM auto logged in as AL Agent. Search policy documents tab for the policy submitted. verify it shows the document on policy document tab for that policy. Verify multi-media tab as well and search the same policy there as well and check forms attached to the policy are present over there.
11 | CPP - PrintMode: HtmlPrint. Create CPP policy. Attach documents on it on documents tab and submit it. Verify it does not show any pdf after submit. Make it cycle run (Host + dap) and upload feeds in AL and access the policy in inquiry after successful archive. Open policy documents in inquiry, it navigates to MM logged in with respect to that perticular policy only. Check Policy documents Tab should be blank. Click on Multi-Media Tab and verify both the attached forms are present over here. Try to open them and verify they opened successfully. Close this MM window. Comes to History tab in inquiry. click on New Business link. verify it again brings back to the same MM window logged in with Perticular policy. Verify policy document is blank and multi media tab contains forms attached to policy. Now open Agent Inbox from tools, from left frame. It opens MM auto logged in as AL Agent. Search policy documents tab for the policy submitted. verify it does not shows any document for that policy. Verify multi-media tab as well and search the same policy there as well and check forms attached to the policy are present over there.
12 | WC - PrintMode: HtmlPrint. Create WC policy. Attach documents on it on documents tab and submit it. Verify it does not show any pdf after submit. Make it cycle run (Host + dap) and upload feeds in AL and access the policy in inquiry after successful archive. Open policy documents in inquiry, it navigates to MM logged in with respect to that perticular policy only. Check Policy documents Tab should be blank. Click on Multi-Media Tab and verify both the attached forms are present over here. Try to open them and verify they opened successfully. Close this MM window. Comes to History tab in inquiry. click on New Business link. verify it again brings back to the same MM window logged in with Perticular policy. Verify policy document is blank and multi media tab contains forms attached to policy. Now open Agent Inbox from tools, from left frame. It opens MM auto logged in as AL Agent. Search policy documents tab for the policy submitted. verify it does not shows any document for that policy. Verify multi-media tab as well and search the same policy there as well and check forms attached to the policy are present over there.
13 | PA - PrintMode: HtmlPrint. Create PA policy. Attach documents on it on documents tab and submit it. Verify it does not show any pdf after submit. Make it cycle run (Host + dap) and upload feeds in AL and access the policy in inquiry after successful archive. Open policy documents in inquiry, it navigates to MM logged in with respect to that perticular policy only. Check Policy documents Tab should be blank. Click on Multi-Media Tab and verify both the attached forms are present over here. Try to open them and verify they opened successfully. Close this MM window. Comes to History tab in inquiry. click on New Business link. verify it again brings back to the same MM window logged in with Perticular policy. Verify policy document is blank and multi media tab contains forms attached to policy. Now open Agent Inbox from tools, from left frame. It opens MM auto logged in as AL Agent. Search policy documents tab for the policy submitted. verify it does not shows any document for that policy. Verify multi-media tab as well and search the same policy there as well and check forms attached to the policy are present over there.
14 | BOP - PrintMode: HtmlPrint. Create BOP policy. Attach documents on it on documents tab and submit it. Verify it does not show any pdf after submit. Make it cycle run (Host + dap) and upload feeds in AL and access the policy in inquiry after successful archive. Open policy documents in inquiry, it navigates to MM logged in with respect to that perticular policy only. Check Policy documents Tab should be blank. Click on Multi-Media Tab and verify both the attached forms are present over here. Try to open them and verify they opened successfully. Close this MM window. Comes to History tab in inquiry. click on New Business link. verify it again brings back to the same MM window logged in with Perticular policy. Verify policy document is blank and multi media tab contains forms attached to policy. Now open Agent Inbox from tools, from left frame. It opens MM auto logged in as AL Agent. Search policy documents tab for the policy submitted. verify it does not shows any document for that policy. Verify multi-media tab as well and search the same policy there as well and check forms attached to the policy are present over there.
15 | DF - PrintMode: HtmlPrint. Create DF policy. Attach documents on it on documents tab and submit it. Verify it does not show any pdf after submit. Make it cycle run (Host + dap) and upload feeds in AL and access the policy in inquiry after successful archive. Open policy documents in inquiry, it navigates to MM logged in with respect to that perticular policy only. Check Policy documents Tab should be blank. Click on Multi-Media Tab and verify both the attached forms are present over here. Try to open them and verify they opened successfully. Close this MM window. Comes to History tab in inquiry. click on New Business link. verify it again brings back to the same MM window logged in with Perticular policy. Verify policy document is blank and multi media tab contains forms attached to policy. Now open Agent Inbox from tools, from left frame. It opens MM auto logged in as AL Agent. Search policy documents tab for the policy submitted. verify it does not shows any document for that policy. Verify multi-media tab as well and search the same policy there as well and check forms attached to the policy are present over there.
16 | Message Center Go to Quote index. Search any accepted policy. Open Message Center for it by clicking on envelop button before it's Applicant Name. Click on Post Message. It opens send message wizard. Enter Underwriter's email in To. Choose an image file and attach it. Enter some content in body and send it. Now Open Media Center and Verify that attached image should be present in Multi Media Tab.
17 | Media Center Go to Quote index. Open any policy. Open Media Center from top. Go to Multi Media Tab and Attach an image there. Verify image attached successfully. Now Open Agent inbox. Search that policy in multi media tab. Verify image attached is present over there.

## MM-Standalone Test
Summary Details -
| % Testing completed | 100
| % Testing remained | 0
| Total Number of Scenarioes | 263
| Total No of Scenrioes passed | 185
| Total No of Scenrioes failed | 0
| % Passed | 70.3422
| % Failed | 0
Scenarioes | Test Cases | Status | Remarks
1.01 | Log on using "cscinbox", "cscpwd" from stand-alone browser, click "Search" icon Click "Multi-Media" tab, verify document list appears. Check Paging and items sorting by clicking over col Labels. | Passed
1.02 | Click filter icon at top right of table to open filter section if needed. Verify "Date Added" entry boxes defaults to a date range that shows the previous 20 years (ok if a few days off), verify only documents in this range are displayed, enter a date range that will show some but not all documents, click search icon and verify results, clear "Date Added" entry boxes, click search icon, verify documents are shown for all dates. | Passed
1.03 | In Description box enter "Report", click search icon, verify all contain "Report" | Passed
1.04 | For "Description" select "a..." (starts with), enter value "d", click search icon, verify all start with d or D | Passed
1.05 | Clear "Description" box value, set "Document Type" to "=" and "Media", click search icon, verify only "Media" | Passed
1.06 | Clear "Document Type", click search icon, click envelope image on the "Vehicle Report" row, verify it retrieves | Passed
1.07 | Click envelope image on the "Demo Photo" row, verify it retrieves | Passed
1.08 | Click "Policy Documents" tab, verify document list appears Check paging and Column's Sorting. | Passed
1.09 | Click filter icon at top right of table to open filter section if needed. Verify "Date Produced" entry boxes defaults to a date range that shows the previous 20 years (ok if a few days off), verify only documents in this range are displayed, enter a date range that will show some but not all documents, click search icon and verify results, clear "Date Produced" entry boxes, click search icon, verify documents are shown for all dates. | Passed
1.1 | Verify the result table recipient column dropdowns do NOT contain "Company" | Passed
1.11 | In Insureds Name box enter "an", click search icon, verify all contain "an" | Passed
1.12 | Clear Insured Name box, click field select icon and select "Pol Eff Date", in "Pol Eff Date" dropdown select "from", enter 12/01/2007 to 01/23/2008, click search icon, verify results by expanding rows to see Pol Eff Date | Passed
1.13 | Clear "Pol Eff Date" boxes, set "Trans Type" to "=" and "EN", click search icon, verify only "EN" | Passed
1.14 | Clear "Trans Type", click search icon, for one of the documents select recipient "Agent", click envelope image in the row, verify "Agent" copy is retrieved | Passed
1.15 | For one of the documents select recipient "Insured", click envelope image in the row, verify "Insured" copy is retrieved | Passed
1.16 | For one of the documents select recipient "All", click envelope image in the row, verify copy with all recipients is retrieved | Passed
1.17 | In the filter area recipient box select "Agent", click search icon, verify all documents are hard coded to Agent, click envelope image in a row, verify "Agent" copy is retrieved | Passed
1.18 | In the filter area recipient box select "All", click "Search", verify all documents are hard coded to All, click envelope image in a row, verify copy with all recipients is retrieved | Passed
1.19 | Select "WIP" tab, verify document list appears. If nothing appears then reset the DocProd CSCDEMO config tables and try again. (See "TestGridNotes.txt" tab, under "CscDemo and XmlDemo DocProd reset") Test Paging and Column's Label Sorting. | Passed
1.2 | Retrieve documents by clicking envelope image in some rows. Click "To Index" to return to the index. | Passed
1.21 | In "Insureds Name" box enter "z", click "Search", verify all contain "z" (list may be empty) | Passed
2 | Log on using "cscinbox2", "cscpwd" from stand-alone browser. Click "Multi-Media" tab, verify document list appears. There should be at most 2 documents per page (Note: For this test, PageSize = 2, ChunkSize = 2) | Passed
2.01 | Click filter icon at top right of table to open filter section if needed. Verify "Date Added" entry boxes defaults to a date range that shows the previous 20 years. Verify only documents in this range are displayed. Enter a date range that will show some but not all documents, click search icon and verify results. Clear "Date Added" entry boxes, click search icon, verify documents are shown for all dates. | Passed
3 | Log on using "sysadmin, "syspwd" from stand-alone browser, select CscDemo Select "Multi-Media" tab, document list should be empty Check paging and sorting by column's labels. | Passed
3.01 | Click filter icon at top right of table to open filter section if needed. Enter "0" for policy, click search icon. If there are multiple pages then test paging using page arrows and page dropdown. If there is only one page then set Success = Y if page arrows are disabled. | Passed
3.02 | In Description box enter "Report", click search icon, verify all contain "Report" | Passed
3.03 | For "Description" select "a..." (starts with), enter value "d", click search icon, verify all start with d or D | Passed
3.04 | Clear "Description" box value, set "Document Type" to "=" and "Media", click search icon, verify only "Media" | Passed
3.05 | Clear "Document Type", click search icon, click envelope image on the "Vehicle Report" row, verify it retrieves | Passed
3.06 | Click envelope image on the "Demo Photo" row, verify it retrieves | Passed
3.07 | Click "Policy Documents" tab, document list should be empty. verify paging and sorting by column's label. | Passed
3.08 | Enter "0" for policy, click search icon, verify the result table recipient column dropdowns contain "Company" | Passed
3.09 | In Insureds Name box enter "an", click search icon, verify all contain "an" | Passed
3.1 | Clear Insured Name box, click select fields icon and select "Pol Eff Date", for "Pol Eff Date" select "from" and enter 12/1/2007 to 1/23/2008, click search icon, verify results by expanding rows and verifying Pol Eff Date. | Passed
3.11 | Clear "Pol Eff Date" boxes, set "Trans Type" to "=" and "EN", click search icon, verify only "EN" | Passed
3.12 | Clear "Trans Type", click search icon, for one of the documents select recipient "Agent", click envelope image in the row, verify "Agent" copy is retrieved | Passed
3.13 | For one of the documents select recipient "Insured", click envelope image in the row, verify "Insured" copy is retrieved | Passed
3.14 | For one of the documents select recipient "All", click envelope image in the row, verify copy with all recipients is retrieved | Passed
3.15 | In filter section Recipient box select "Agent", click search icon, verify all documents are hard coded to Agent, click envelope image in a row, verify "Agent" copy is retrieved | Passed
3.16 | In filter section recipient box select "All", click search icon, verify all documents are hard coded to All, click envelope image in a row, verify copy with all recipients is retrieved | Passed
3.17 | Select "WIP" tab, document list should be empty Check paging and sorting by column's label. | Passed
3.18 | Enter "0" for policy, click search icon, retrieve documents by clicking envelope images in some rows. If nothing appears then reset the DocProd CSCDEMO config tables and try again. (See "TestGridNotes.txt" tab, under "CscDemo and XmlDemo DocProd reset") | Passed
3.19 | In "Insureds Name" box enter "h", click search icon, verify all contain "h" | Passed
3.2 | For "Insured Name" select "from" and enter "h" to "m", click search icon, verify all between h and m | Passed
4 | Log on using "cscinbox", "cscpwd" from stand-alone browser, Click "Multi-Media" tab, list of documents should appear, click search icon | Passed
4.01 | Click "+" icon, verify attach row appears below table, verify "+" icon is disabled, verify hardcoded "date added" in attach row | Passed
4.02 | Click cancel icon in attach row, verify attach row disappears, verify "+" icon is enabled | Passed
4.03 | Click "+" icon, click attach icon, verify warning "Missing Policy or Quote. Missing Document Type. Missing Description. Missing Security. No file selected." | Passed
4.04 | Browse to "demo.pdf" file, click attach icon, verify alert "Missing Policy or Quote. Missing Document Type. Missing Description. Missing Security." | Passed
4.05 | Enter data for Policy, Document Type, Description, Security, Notes | Passed
4.06 | Click attach icon, verify attached document automatically appears in search table | Passed
4.07 | Click envelope for new document to open and verify PDF document is displayed | Passed
4.08 | Attach a JPG document "demo.jpg", verify you can retrieve it | Passed
4.09 | Attach a document > 5 MB "demo-over5MB.txt", verify you can retrieve it | Passed
4.1 | Attach an invalid document "demo.exe", verify "Media Management Error" that reads "Files with extension (exe) cannot be imported", verify the document was not attached | Passed
5 | M9: Ability to soft delete and change document access level. Log on using "sysadmin", "syspwd". Select CscDemo and Multi-Media tab. Set the footer "Display" dropdown to "Normal". For Policy enter "0" and click search icon. Verify that the More menu "Hide" item is disabled. | Passed
5.01 | Choose a row and click the "Hide" icon. Verify that the row disappears. | Passed
5.02 | Check two documents. Verify that the More menu "Hide" item is enabled. * Click the More menu "Hide" item. In the dialog click the top right "X" button. Verify the dialog closes and the documents are still there. * Click the More menu "Hide" item. In the dialog click "Cancel". Verify the dialog closes and the documents are still there. * Click the More menu "Hide" item. In the dialog click "Hide". Verify that the checked rows disappear. | Passed
5.03 | Set the footer "Display" dropdown to "All w/ hidden". Verify that all documents, both hidden and unhidden, are visible. Verify that there is no "Hide" or "UnHide" item in the More menu. | Passed
5.04 | Set the footer "Display" dropdown to "Hidden Only". Verify that only the hidden documents are visible. Verify that there is a More menu "UnHide" item that is disabled. | Passed
5.05 | Choose a row and click the "UnHide" icon. Verify that the row disappears. | Passed
5.06 | Check two documents. Verify that the More menu "UnHide" button is enabled. * Click the More menu "UnHide" item. In the dialog click the top right "X" button. Verify the dialog closes and the documents are still there. * Click the More menu "UnHide" item. In the dialog click "Cancel". Verify the dialog closes and the documents are still there. * Click the More menu "UnHide" item. In the dialog click "UnHide". Verify that the checked rows disappear. | Passed
5.07 | Set the footer "Display" dropdown to "Normal". Verify that the documents you just used UnHide on are in the results table. | Passed
6 | Log on using "sysadmin", "syspwd". Select CscDemo and Multi-Media tab. For Policy enter "0" and click the search icon. Verify that the More menu "Set Access" item is disabled. | Passed
6.01 | Check two documents with access level of "Agent". Verify that the More menu "Set Access" item is enabled. * Click the More menu "Set Access" item. In the dialog click the top right "X" button. Verify the dialog closes and page does not change. * Click the More menu "Set Access" item. In the dialog click "Cancel". Verify the dialog closes and page does not change. * Click the More menu "Set Access" item. Verify that the dialog "Set Access" button is disabled. In the dialog dropdown select "Admin". Verify that the dialog "Set Access" button is enabled and click the button. Verify that access level for these documents changes to "Admin". * Check the "Admin" documents. Click the More menu "Set Access" item. In the dialog dropdown select "Agent". In the dialog click the "Set Access" button. Verify that the documents now have access level "Agent". | Passed
7 | ABILITY TO EDIT NOTES (user cscinbox) - CSCDEMO (MCR) Log on using "cscinbox", "cscpwd" from stand-alone browser, click "Search" icon, click "Multi-Media" tab, list of documents should appear | Passed
7.01 | Expand a row that has an empty note value, click "Edit" icon, verify edit mode opens, enter a note, click "Cancel" icon, verify the note value is still blank | Passed
7.02 | Expand a row that has an empty note value, click "Edit" icon, verify edit mode opens, enter a note, click "Update", verify the note value was set correctly | Passed
7.03 | Expand this row, click "Edit" icon, modify the note, click "Cancel", verify the note was not changed | Passed
7.04 | Expand this row, click "Edit" icon, modify the note, click "Update", verify the note was changed | Passed
8 | ABILITY TO PERFORM WIP TASKS - CSCDEMO (logon using sysadmin,syspwd) | Passed
8.01 | Click envelope image for a WIP document to open, verify it opens. If no WIP documents are available then reset the DocProd CSCDEMO config tables and try again. (See "TestGridNotes.txt" tab, under "CscDemo and XmlDemo DocProd reset") | Passed
8.02 | Select "Agent" recip, verify "NO FORMS WERE GENERATED", select "Insured" recip, verify WIP test form | Passed
8.03 | Click "To Index", verify return to index. | Passed
8.04 | Open WIP document, click "Preview", verify PDF version | Passed
8.05 | Click "Edit" verify HTM version | Passed
8.06 | Open WIP document, select "Insured" recip, modify document, click "Save", verify changes are still there, click "To Index" and reopen document, verify changes are still there, click "Preview", verify changes are still there | Passed
8.07 | Open WIP document, select "Insured" recip, modify document, click "To Index", verify "changes were made" alert, click "Cancel", verify stay on HTM page | Passed
8.08 | Open WIP document, select "Insured" recip, modify document, click "To Index", verify "changes were made" alert, click "No", verify go to WIP index, reopen document, verify changes were NOT saved | Passed
8.09 | Open WIP document, select "Insured" recip, modify document, click "To Index", verify "changes were made" alert, click "Yes", verify go to WIP index, reopen document, verify changes are saved | Passed
8.1 | Open WIP document, select "Insured" recip, modify document, click "Preview", verify "changes were detected" alert, click "Cancel", verify stay on HTM page | Passed
8.11 | Open WIP document, select "Insured" recip, modify document, click "Preview", verify "changes were detected" alert, click "No", verify go to PDF page and changes are NOT saved | Passed
8.12 | Open WIP document, select "Insured" recip, modify document, click "Preview", verify "changes were detected" alert, click "Yes", verify go to PDF page and changes are saved | Passed
8.13 | Open WIP document, click "Preview", click "To Index", verify return to index | Passed
8.14 | Open WIP document, click "Preview", click "Immediate Print", click "Cancel" on "complete transaction" dialog, verify remain on PDF page | Passed
8.15 | Click "Policy Document" tab, for Policy enter "HP" and search, note the number of documents, click WIP tab, open a WIP document, click "Preview", click "Immediate Print", click "OK" on "complete transaction" dialog, verify "successfully archived" message, click OK, verify you go to the WIP index page, verify WIP document is not listed any more, click "Policy Documents" tab, verify that the document you sent to archive now appears here, open it with "Insured" selected, verify correct | Passed
8.16 | Open WIP document, click "Preview", click "Batch Print", click "Cancel", verify remain on PDF page | Passed
8.17 | Open WIP document, click "Preview", click "Batch Print", click "OK", verify "has been queued" message, click "OK", verify on WIP index page, in SQL WIP table verify STATUSCODE = "B" (not "W") | Passed
8.18 | Use userid 'sysadmin' and open a WIP document. From another browser using userid 'sysadmin' try to open the same WIP document. Verify "This WIP document is locked by your userid 'sysadmin'. Do you want to end the old session and start a new one?". Click "cancel" and verify remain on index search screen. | Passed
8.19 | Use userid 'sysadmin' and open a WIP document. From another browser using userid 'sysadmin' try to open the same WIP document. Verify "This WIP document is locked by your userid 'sysadmin'. Do you want to end the old session and start a new one?". Click "OK" and verify that it opens. Verify that this second WIP document is functional (change recipient, click Preview). On the first WIP document change the recipient and verify a "document locked" error. | Passed
8.2 | Use userid 'sysadmin' and open a WIP document. From another browser using userid 'cscadmin' try to open the same WIP document. Verify "This WIP document is locked by userid 'sysadmin'." | Passed
8.21 | Open a WIP document again. In the Tools nav area click the "WIP Admin" icon. Click search. One item should appear. Expand the row. Click "delete" then "Cancel" and verify that nothing happens. Click "delete" then "OK" and verify table is empty. Go back to the WIP document page and change the recipient and verify "Invalid WIP access by userid 'sysadmin. This WIP document is not currently open." | Passed
8.22 | Open a WIP document, click "Delete", verify confirm dialog, click "Cancel", verify nothing happens, click "Delete", verify confirm dialog, click OK, verify successfully deleted dialog, click OK, verify WIP index has appeared and that the deleted WIP document is not in the index table. | Passed
9 | ABILITY TO PERFORM MANUAL FORMS TASKS - XMLDEMO Go to XMLDEMO Manual Forms tab, enter "CSC" for Group1, click search icon, verify results, verify "Generate" button is disabled. | Passed
9.01 | Check a row and verify "Generate" button is enabled. | Passed
9.02 | Check only "Auser 0410", click "Generate" button, verify PDF Manual Forms page with "Add Forms" and "Archive" buttons only | Passed
9.03 | Click "Add Forms" from this PDF page and verify go to Manual Forms index page | Passed
9.04 | Check only "Form 3w", click "Generate" button, verify HTM Manual Forms page with "Add Forms", "Spell", "To WIP" and "Preview" buttons only | Passed
9.05 | Click "Preview", verify PDF Manual Forms page with "Add Forms", "Archive" and "Edit" buttons only | Passed
9.06 | Click "Edit", verify back on HTM Manual Forms page | Passed
9.07 | Click "Add Forms" from this HTM page and verify go to Manual Forms index page | Passed
9.08 | Go to Policy Documents enter "1" for policy and do a search, make a note of how many documents appear. It is okay if there are none (DO NOT mark this as a failure if there are none!). Go to Manual Forms, check only "Auser 0410", click "Generate" button, verify a PDF appears, click "Archive", verify "successfully archived" message, click OK, verify all buttons disabled, go to "Policy Documents" tab, verify document is there without having to click search. | Passed
9.09 | Log into Media Management again and select XmlDemo. Go to WIP enter "1" for policy and do a search, make a note of how many documents appear. It is okay if there are none (DO NOT mark this as a failure if there are none!). Go to Manual Forms, for Group1 enter "csc" and click the search icon, check only "Test Wip Form", click "Generate" button, verify editable HTM appears, click "To WIP", verify "successfully sent to WIP" message, click OK, verify all buttons disabled, go to "WIP" tab, verify document is there without having to click search. | Passed
10 | ABILITY TO PERFORM SPELL CHECK TASKS - CSCDEMO, XMLDEMO Open a WIP document, enter "test" in a textbox, click "Spell" button, verify Spelling Check alert with message "No spelling problems found". | Passed
10.01 | Open a WIP document, enter "helo world tesst" in a textbox, click "Spell" button, verify spell dialog opens, for "helo" click "Ignore", for "tesst" choose "test" and click "Change", verify spell dialog closes, verify textbox contains "helo world test" | Passed
10.02 | Open a WIP document, enter "helo world tesst" in a textbox, click "Spell" button, for "helo" click "Cancel", verify spell check box closes, verify textbox still contains "helo world tesst" | Passed
10.03 | Open a WIP document, enter "CSC" in a textbox, click "Spell" button, for "CSC" click "Add", verify spell dialog closes, verify "CSC" in textbox still, click "Spell" button again, verify immediately get Spelling Check alert with message "No spelling problems found". (NOTE: may need to use "CSC2", etc) | Passed
10.04 | Open a manual form document, enter "test" in a textbox, click "Spell" button, verify Spelling Check alert with message "No spelling problems found". | Passed
10.05 | Open a manual form document, enter "helo world tesst" in a textbox, click "Spell" button, verify spell dialog opens, for "helo" click "Ignore", for "tesst" choose "test" and click "Change", verify spell dialog closes, verify textbox contains "helo world test" | Passed
10.06 | Open a manual form document, enter "helo world tesst" in a textbox, click "Spell" button, for "helo" click "Cancel", verify spell check box closes, verify textbox still contains "helo world tesst" | Passed
10.07 | Open a manual form document, enter "CSC" in a textbox, click "Spell" button, for "CSC" click "Add", verify spell dialog closes, verify "CSC" in textbox still, click "Spell" button again, verify immediately get Spelling Check alert with message "No spelling problems found". (NOTE: may need to use "CSC2", etc) | Passed
11 | ABILITY TO ACCESS INDEX WITH SINGLE LIST FOR MCR,DAP,WIP - PageDemo Select "Page Small", in "Policy" enter "0", click search icon, verify document list Verify paging and sorting by column's label. | Passed
11.01 | For "Insureds Name", select operation "a…" (Starts With), enter value "m", click search icon, verify all start with m | Passed
11.02 | Clear Insureds Name, for "Date Produced" select operation "from", enter 11/30/2007 to 1/2/2008, click search icon, verify all results are in date range | Passed
11.03 | Select "Page Big", in "Policy" enter "0", click search icon, verify document list | Passed
11.04 | Test paging using page arrows and page dropdown | Passed
11.05 | Click "Insureds Name" label and verify sorting, verify up and down triangles change | Passed
11.06 | For "Insureds Name", select operation "a…" (Starts With), enter value "m", click search icon, verify all start with m | Passed
11.07 | Clear Insureds Name, for "Date Produced" select operation "from", enter 11/30/2007 to 1/2/2008, click search icon, verify all results are in date range | Passed
12 | ABILITY TO USE MULTI-DOC RETRIEVAL - CscDemo Using "CscDemo" and "Policy Documents" set Policy to "0" and search, with nothing checked verify More menu is collapsed, expand More menu and verify "View" item is disabled, collapse More menu | Passed
12.01 | Check header check box and verify all rows are checked, verify More menu automatically expands and "View" item is enabled | Passed
12.02 | Uncheck header checkbox and verify all rows are unchecked, verify More menu is collapsed, expand More menu and verify "View" item is disabled, collapse More menu | Passed
12.03 | Check a row checkbox, verify More menu automatically expands and "View" item is enabled | Passed
12.04 | Check several documents with different recipients (some "All), on More menu click "View", verify PDF appears with all documents with requested recipients | Passed
12.05 | Using "CscDemo" and "Multi-Media" set Policy to "0" and search, with nothing checked verify More menu is collapsed, expand More menu and verify "View" item is disabled, collapse More menu | Passed
12.06 | Check a single row, verify that More menu automatically expands and "View" item is enabled | Passed
12.07 | Verify that More menu "View" item is enabled when multiple documents all with black checks are selected | Passed
12.08 | Verify that More menu "View" item is enabled when exactly one document is checked and it has a red check | Passed
12.09 | Verify that More menu "View" item is disabled when more than one document is checked and there is at least one red check | Passed
13 | ABILITY TO USE FILTERING - FILTERDEMO Log on as "sysadmin,syspwd" (Internal), select "FilterDemo", verify only have option bar buttons: Multi-Media,Policy Documents,WIP, Policy Documents RF, Admin Pages, Log Pages | Passed
13.01 | Select "Policy Documents, verify recipients dropdown contains only: Agent, Company, Insured, Notices, All | Passed
13.02 | Do Multi-Media search with Policy = "0". Click "+" icon and verify that the access level dropdown contains Agent, CSR and Admin. Verify that you see Agent, CSR and Admin documents in the list. If you do not see all of these then edit some documents so that they have the missing security values and verify that they appear. | Passed
13.03 | Log on as "sysexternal,syspwd" (external), Select "FilterDemo", verify only have option bar buttons: Multi-Media,Policy Documents,WIP, Policy Documents RF, Admin Pages, Log Pages | Passed
13.04 | Select "Policy Documents", verify recipients dropdown contains only: Agent, Insured, Notices, All | Passed
13.05 | Do Multi-Media search with Policy = "0", Verify see only Agent | Passed
13.06 | Log on as "systest,syspwd" (test), select "FilterDemo", verify only have tabs: Policy Documents,WIP, Policy Documents RF, Admin Pages, Log Pages | Passed
13.07 | Verify recipients dropdown contains only: Insured, Notices, All | Passed
13.08 | Select "Policy Documents RF", search for policy = "0", verify APV000028300 doc allows recipients: Agent, Insured and All. Also select "All" and double click to retrieve and verify that Agent and Insured are in the PDF. | Passed
13.09 | Verify CPK000000101 doc allows only Agent, Insured and All (Company not found). Also select "All" and double click to retrieve and verify that Agent and Insured only are in the PDF. | Passed
13.1 | Verify PGS012408000 doc allows only Insured and All (Agent, Company not found). Also select "All" and double click to retrieve and verify that only Insured is in the PDF. | Passed
14 | TEST DOCUMENT VIEWED INDICATOR Log on using "sysadmin, "syspwd" from stand-alone browser, select CscDemo, select Multi-Media, enter "0" for policy, click "Search", list of documents should appear. | Passed
14.01 | Expand rows for all documents at least 1 month old and verify that "Date Viewed" value is equal to "before" followed by the date one month ago. Verify no flag in Viewed column. | Passed
14.02 | Attach a new document, verify that it appears in the table, expand and verify it has an empty "Date Viewed", verify an envelope with a flag in the Viewed column | Passed
14.03 | Click envelope image of the new document to open it, close document window, expand and verify "Date Viewed" is set to current date, verify an envelope with no flag in Viewed column | Passed
14.04 | Enter 00 for policy, click "Search" button, verify page reloads, expand attached doc and verify "Date Viewed set to current date, verify envelope with no flag in Viewed column | Passed
14.05 | Attach a new document, expand and verify that it appears in the table, verify it has an empty "Date Viewed", verify an envelope with a flag in the Viewed column | Passed
14.06 | Check the new document along with some other documents, click "View" to open them, close document window, expand and verify "Date Viewed" is set to current date, verify an envelope with no flag in Viewed column | Passed
14.07 | Click "Search", verify page reloads, expand and verify "Date Viewed set to current date, verify envelope with no flag in Viewed column | Passed
14.08 | Attach several new documents, click the Envelope column top sort button, verify documents are sorted with red flags all at the top. | Passed
15 | ABILITY TO SEARCH MEDIA MANAGEMENT LOGS For 28.01 thru 28.09 do the following: click "Search" and verify, click RecordModifyTs, change the date range, click "Search" and verify (do this again and choose a valid date range if no records appear), in the AppConfigList box enter "CscDemoMcr", click "Search" and verify | Passed
15.01 | In option bar select "Log Pages, Search", verify "Log Search" page opens, test this page | Passed
15.02 | In option bar select "Log Pages, AppSearch", verify "Log AppSearch" page opens, test this page | Passed
15.03 | In option bar select "Log Pages, Get", verify "Log Get" page opens, test this page | Passed
15.04 | In option bar select "Log Pages, Delete", verify "Log Delete" page opens, test this page | Passed
15.05 | In option bar select "Log Pages, Attach", verify "Log Attach" page opens, test this page | Passed
15.06 | In option bar select "Log Pages, Update", verify "Log Update" page opens, test this page | Passed
15.07 | In option bar select "Log Pages, Save", verify "Log Save" page opens, test this page | Passed
15.08 | In option bar select "Log Pages, Error", verify "Log Error" page opens, test this page | Passed
15.09 | In option bar select "Log Pages, User", verify "Log User" page opens, test this page | Passed
15.1 | On Search log page do a search, click on an "AppSearch" link, verify AppSearch table appears with appropriate rows (RecordModifyTs should be close), click "Search" and "AppSearch" tabs to switch between "Search" and "AppSearch" views | Passed
15.11 | On AppSearch log page do a search, click on a "Search" link, verify Search table appears with a single matching row (RecordModifyTs should be close), click "Search" and "AppSearch" tabs to switch between "Search" and "AppSearch" views | Passed
15.12 | On Search (or another log table) do a search with Status = "F", click on an "Error" link, verify Error table appears with appropriate rows (RecordModifyTs should be close), click "Error" tab and the other tab to switch between "Error" and the other view | Passed
15.13 | On Error log page do a search, click on one of the links in the "Parent" column and verify the parent table opens with a row, click "Error" tab and the other tab to switch between "Error" and the other view | Passed
16 | Ability to administer user settings Select "Admin Pages, User Admin", verify the "Users Admin" page appears, create user "zinbox" using Authority Level = "Inbox", Filter = "internal", Source = "CscDemoSrc", Org = "CSC", Agent Id = "0000358", Agency Id = "1800000", IsMasterAgent = False. Make sure you copy the password. Verify successful and that "zinbox" appears in the list of users when you search. | Passed
16.01 | Login using "zinbox", enter the new password, click "Submit". Verify that a "Must change password" alert appears, click OK. Verify that the "Change Password" box is now checked and two new password boxes are provided. Enter "zzzpwd" in the new password boxes and click "Submit". Verify successful login. | Passed
16.02 | Verify that the search pages do an initial search using agent number, verify that the option bar does NOT contain "Admin Pages" or "Log Pages". | Passed
16.03 | Go to the Users page and create user "zpower" using Authority Level = "PowerUser", Filter = "internal", Source = "CscDemoSrc", Org = "CSC", Agent Id = "111", Agency Id = "111", IsMasterAgent = False. Make sure you copy the password. Verify successful and that "zpower" appears in the list of users when you search. | Passed
16.04 | Login using "zpower", enter the new password, click "Submit". Verify that a "Must change password" alert appears, click OK. Verify that the "Change Password" box is now checked and two new password boxes are provided. Enter "zzzpwd" in the new password boxes and click "Submit". Verify successful login. | Passed
16.05 | Verify that no initial search is done. Verify that the option bar does NOT contain "Admin Pages" or "Log Pages". Verify that you can do a general search for any documents. | Passed
16.06 | Go to the Users page and create user "zadmin" using Authority Level = "Admin", Filter = "internal", Source = "CscDemoSrc", Org = "CSC", Agent Id = "111", Agency Id = "111", IsMasterAgent = False. Make sure you copy the password. Verify successful and that "zadmin" appears in the list of users when you search. | Passed
16.07 | Login using "zadmin", enter the new password, click "Submit". Verify that a "Must change password" alert appears, click OK. Verify that the "Change Password" box is now checked and two new password boxes are provided. Enter "zzzpwd" in the new password boxes and click "Submit". Verify successful login. | Passed
16.08 | Verify that no initial search is done, verify that the option bar contains both "Admin Pages" and "Log Pages". Verify that you can do a general search for any documents. | Passed
16.09 | RACF User Id test - Login using zadmin, aaa (wrong password) four times. Verify that first 3 times get alert "Invalid Password". Verify on 4th time get alert "User zadmin has been locked out or deactivated...". Next login using sysadmin,syspwd, go to "Admin Pages, User Admin", search for "zadmin", expand the "zadmin" row, click "Edit", change Status to Active, and click "Update". Try to log on using "zadmin", "zzzpwd" and verify that you can log on now. | Passed
16.1 | Go to Login page, enter nothing, click "Submit", verify alert "Please enter a userid and password" | Passed
16.11 | Check "Change Password", enter nothing, click "Submit", verify alert "Please enter a userid and all passwords" | Passed
16.12 | Enter userid "zadmin", password "zzzpwd", click "Submit", verify alert "Please enter a userid and all passwords" | Passed
16.13 | Enter different values for new password and verify new password, click "Submit", verify alert "New password and verify new password are not the same" | Passed
16.14 | Enter "zzzpwd" for both new password and verify new password, click "Submit", verify alert "New password is the same as the old password. Must enter a different new password." | Passed
16.15 | Enter "zzzpwd2" for both new password and verify new password, click "Submit", verify successful. Login again using user "zadmin" and new password "zzzpwd2", verify successful. | Passed
16.16 | Go to "Admin Pages, UserAdmin, search for "zadmin", expand "zadmin" row, click "Edit", change status to "Disabled", click "Update", verify successful. Try to log on using zadmin,zzzpwd2, verify alert "UserId is locked." Go to "Admin Pages, User Admin" and change the status back to "Active". Verify "zadmin" can now login. | Passed
16.17 | Go to "Admin Pages, User Admin", search for "zadmin", expand "zadmin" row, click "Delete", on popup verification click OK, verify successful and "zadmin" disappears from the user list. Try to log on using zadmin, verify alert "Invalid login." | Passed
16.18 | Go to "Admin Pages, User Admin". Search for users using various search criteria and verify results. | Passed
16.19 | Test Alerts: Perform a search that lists some users, click the "+" button, leave all fields empty, click the attach "paperclip" button, verify alert specifying missing fields, for the UserId value enter one of the existing UserId's in the table, enter values for the rest of the fields, click the attach "paperclip" button, verify "UserId already exists" warning box. | Passed
17 | ABILITY TO ADMINISTER SSO USERS (use SSO URL) Create with existing SSO user: Go to "Admin Pages, User Admin" page, in UserId entry enter "sso" and search, click "+" button, enter UserID "ssoold", enter other field values but leave the password box blank, click Attach icon, verify that there was no alert or error, verify that "ssoold" automatically appeared in the table, open a new browser and log in using "ssoold" and verify the login works, close new browser | Passed
17.01 | Delete user: Expand the "ssoold" row, click "Delete", click "OK" in the "are you sure" dialog, verify "ssoold" was automatically removed from the table, open a new browser and log in using "ssoold", verify error with "Error details not available for this user." | Passed
17.02 | Create with new SSO user: Go to "Admin Pages,User Admin" page, in UserId entry enter "sso" and search, click "+" button, enter UserID "ssonew", enter other field values, click the password "Reset" icon to generate a password, click Attach icon, verify that there was no alert or error, verify that "ssonew" automatically appeared in the table, open a new browser and log in using "ssonew" and verify the login works, close new browser | Passed
17.03 | Update password: Click "Edit" for "ssotest", click password "Reset" icon, click "Update" icon, verify result table appears with no error message, open a new browser and log in using "ssotest" with new password and verify the login works, close new browser | Passed
18 | UX UI Testing Login as cscinbox, verify document search page appears and option bar contains only: Multi-Media, Policy Documents, WIP, Multi Attach | Passed
18.01 | Login as cscpower, verify document search page appears and option bar contains only: Multi-Media, Policy Documents, WIP, Multi Attach | Passed
18.02 | Login as sysadmin, verify document search page appears and option bar contains only: Multi-Media, Policy Documents, WIP, Multi Attach, Admin Pages, Log Pages | Passed
18.03 | Click the "My Apps" link at the top of the page and verify the "My Apps" page appears | Passed
18.04 | Click the "Media Management" app button and verify the document search page appears | Passed
18.05 | Click the "My Apps" link to go to the "My Apps" page. Click the "Wikonnect" app button and verify that the CSC Global Pass logon page appears. Log on with your user ID and verify the Wikonnect web page appears. | Passed
18.06 | Change Config dropdown to XmlDemo and verify config changes (doc search should have Manual Forms tab), change it back to CscDemo and verify changes back to CscDemo. | Passed
18.07 | Click option bar buttons and menu items and verify pages appear as expected. | Passed
18.08 | On a search page click the filter icon several times. Verify that each time it either hides or shows the filter section. Show the filter section and click the "close filter" icon. Verify that the filter section closes. | Passed
18.09 | Select ErrDemo and perform a policy document search. Verify that an error box slides in from the left. Click the "Expand" icon to expand the error details. Click the "Collapse" icon to collapse the error details. Click "Close" and verify that the error box slides off the screen. | Passed
18.1 | Click the "About" link at the top right of the page. Verify that the alert box appears. Click each row twice and verify it expands and then collapses. Verify that when expanded, the "About our CSC Media Management software" row contains a Media Management Version number and an environment description. Click outside of the about box and verify that it dissappears. | Passed
19 | Multi-Attach page section Login with "cscinbox" user id. Go to "Multi-Media" search page and verify some documents are in the result table. Go to "Multi Attach" page. Attach 3 docments, remove middle one and now click on "Attach All" button. Verify that the RESULTS is selected now and results table contains two rows with data in the fields. Go to "Multi Media" search page and verify that the result table automatically updates to contain the attached documents. Retrieve one of the new attached documents. | Passed
19.01 | Login with "sysadmin" user id and make sure CscDemo is selected. Go to "Multi-Media" search page and perform a search that has some documents in the result table. Go to "Multi Attach" page. Attach 3 docments (make sure they satisfy your previous search conditions), remove middle one and now click on "Attach All" button. Verify that the RESULTS is selected now and the results table contains two rows with data in the fields. Go to "Multi Media" search page and verify that the result table automatically updates to contain the attached documents. Retrieve one of the new attached documents. | Passed
20 | Firefox & Chrome browser testing Index Search on Multi-Media then retrieval any document | Passed
20.01 | Attach a document in Multi-Media repository. Verify by doing fresh search | Passed
20.02 | Perform search for Policy document and then retreival any document | Passed
20.03 | Perform search in WIP then open any WIP document | Passed
20.04 | Open any WIP document, click on "To Index" buttion. It should display wip search page. | Passed
20.05 | Open any WIP document, In HTML version, enter word "tesk" and click on "Spell" buttion. In popup box , select correct entry and click OK. Popup should get closed and it should change spelling in HTML form. | Passed
20.06 | Open any WIP document, Enter any word then click on "Save" buttion. Goback to search page and perform search again. Open same WIP document and verify. It should have that value. | Passed
20.07 | Open any WIP document, click on view "Delete" buttion. | Passed
20.08 | Open any WIP document, click on "Preview" buttion. PDF version should get display | Passed
20.09 | Manual Forms search, select all, open Manual Forms doc | Passed
20.1 | Manual Forms - Perform Search and verify result | Passed
20.11 | Manual Forms open any form and verify Spell check functionality. | Passed
20.12 | Manual Forms open any form and verify "To Wip" functionality. | Passed
20.13 | Manual Forms open any form and verify "Preview" functionality. Document should display in PDF version. | Passed
20.14 | Multi-Attach page - attach 2 documents then go to multimedia search and perform a fresh search. Now verify. | Passed
21 | Agent Reassignment Login to Media Management - sysadmin,syspwd. Click "Admin Pages" and in menu click "Agent Reassignment". Verify the Agent Reassignment page appears. | Passed
21.01 | Click on "+" icon. It should display the row with Attach and Cancel icons. The "+" icon button should be disabled. | Passed
21.02 | Click on Cancel icon. Attach section should disappear and "+" icon should be enabled. | Passed
21.03 | In the "User Agent Id" box enter "0" and click search icon. Verify that some rows appear in the result table. Click on some column headers and verify that the columns sort correctly. | Passed
21.04 | Click the "+" icon. In the expanded section enter "000" for the User Agent Id and enter some values for the other fields. Click "Attach" and verify that the row is automatically added to the result table. | Passed
21.05 | On the row you added click the "Edit" icon and verify you enter edit mode for the row. Click the "Cancel" icon and verify the row is unchanged. | Passed
21.06 | On the row you added click the "Edit" icon and change some field values. Click the "Update" icon and verify the fields are changed. | Passed
21.07 | For the row you added, click the "Delete" icon and verify that the row is deleted. | Passed
22 | Email Document Log on using sysadmin,syspwd. Select CscDemo and click the "Multi-Media" tab. Perform a search that displays some documents. Verify that the rows contain a "Send Email" icon in the Actions column. | Passed
22.01 | Choose a row and click on the "Send Email" Icon. The Email Attachment dialog should appear. Verify that the Subject textbox contains "Attachment for" followed by the document number. | Passed
22.02 | Choose a row and click on the "Send Email" icon to open the email dialog. Click the "Cancel" button and verify that the email dialog closes. | Passed
22.03 | Choose a row and click on the "Send Email" icon to open the email dialog. Enter some invalid email addresses. Click "Send" and verify that an alert appears indicating that the email addresses are invalid. | Passed
22.04 | Choose a row and click on the "Send Email" icon to open the email dialog. Empty all of the entry boxes. Click "Send" and verify that an alert appears indicating what entries are required. | Passed
23 | M6: Abilty To View Thumbnails - CscDemo (IE) Using an IE browser (at least IE 8, prefer IE 10), log on as Administrator from stand-alone browser using “sysadmin,syspwd”. Select "CscDemo" and "Multi-Media" tab. Enter "0" for policy, click "Search". Search results for policies should get displayed. Note: For attach use files in "\\cscfilbly002\base\CSCBase\MediaView\MMRoot\Other\TestFiles" | Passed
23.01 | Click "New". Attach a PDF document. Verify attached document automatically appears in search table. Verify the correct Icon for "Document" type appears under the "File" column. Hover over the icon and verify that the generic document thumbnail appears. Click the icon and verify that the document is retrieved. | Passed
23.02 | Click "New". Attach a file of type "avi". Verify attached document automatically appears in search table. Verify the correct Icon for "Video" type appears under the "File" column. Hover over the icon and verify that the generic video thumbnail appears. Click the icon and verify that the document is retrieved. | Passed
23.03 | Click "New". Attach a file of type "wav". Verify attached document automatically appears in search table. Verify the correct Icon for "Audio" type appears under the "File" column. Hover over the icon and verify that the generic audio thumbnail appears. Click the icon and verify that the document is retrieved. | Passed
23.04 | Click "New". Attach a file of type "ini". Verify attached document automatically appears in search table. Verify the correct Icon for "Other" type appears under the "File" column. Hover over the icon and verify that the generic other thumbnail appears. Click the icon and verify that the document is retrieved. | Passed
23.05 | Click "New". Attach a file of type "jpg". Verify attached document automatically appears in search table. Verify the correct Icon for "Image" type appears under the "File" column. Hover over the icon and verify that a small version of the image appears as a thumbnail. Click the icon and verify that the image is retrieved. | Passed
23.06 | Click "New". Attach image files of types "bmp", "gif" and "png". Verify attached document automatically appears in search table. Verify the correct Icon for "Image" type appears under the "File" column. Hover over the icon and verify that a small version of the image appears as a thumbnail. | Passed
23.07 | Sort by clicking "File" header label . Verify sorting and up and down red triangles change to indicate sort direction. Also verify with up red triangle that the File Type are in order "Document", "Image", "Video", "Audio" and "Other". Click the "File" header label again and verify sorting in reverse order. | Passed
24 | BridgeMcr recipient mode Search: Log on using "sysadmin,syspwd". Select Config "RecipDemo". Perform a search and verify successful. Click a column to sort by it and verify successful. | Passed
24.01 | Retrieve: Select a recipient for a document and retrieve. Verify correct recipient was retrieved. Repeat for other recipients. | Passed | Unable to retrieve due to empty Repository
25 | Multi File Browse Browse: Log on using "sysadmin,syspwd". Select Config "CscDemo" and click "Multi Attach" tab. Verify "File Count: 0 of 10" at top right of roster. Click "Add files" icon and select three files. Verify that a row is created for each file. Verify "File Count: 3 of 10" at top right of roster. | Passed
25.01 | Enter Fields: Enter field values for the first row. Click "Copy" icon and verify that the "Paste All" button is enabled. Click "Paste All" and verify that the field values were pasted into the other two rows. Modify the row Description values so that they are different. | Passed
25.02 | Change File: Expand the first row. Click "Change File" icon in detail area. Verify file select dialog appears. Select a replacement file. Verify that the new file name appears in the expanded row. | Passed
25.03 | Remove Row: Expand the third row and click "Remove" icon. Verify that the row is removed. Verify "File Count: 2 of 10" at top right of roster. | Passed
25.04 | Attach: Click "Attach All". Verify that the PENDING tab is disabled and the RESULTS tab is enabled. Verify that the files appear in the RESULTS table with Status "Success". Click the PENDING tab and verify empty table. Perform a search in Multi-Media and verify that the files are there. | Passed
25.05 | Alerts: Click the "New Files" button and select more than 10 files. Verify that an alert appears. Add some files to the PENDING table. Use "Attach All" without entering field values. Verify an alert appears. | Passed
26 | Globalization - Date Formats Set your browser language preference to "Russian [ru]". Log on using "sysadmin,syspwd". Select Config "CultureDemo" and select "Multi-Media". Do a search and verify dates use format "dd.mm.yyyy". In the entry section, for "Date Added" click the calendar and select a valid date. Verify date appears as "dd.mm.yyyy". Search and verify results. | Passed
26.01 | Do a search and find an unread document with a red flag (attach a new doc if needed). Verify that Date Viewed is empty. Click envelope to open. Close document. Verify that Date Viewed is set to current date with format "dd.mm.yyyy". | Passed
27 | Personalize For the below tests login with "sysadmin" user id and select CscDemo. | Passed
27.01 | Click on "My Apps". Verify "My Apps" page appears. Click the "Media Management" icon and verify that the Media Management window appears. | Passed
27.02 | Click on "My Apps". Verify "My Apps" page appears. Click the "Wikonnect" icon. It will take you to the Wikonnect page where you can perform search. | Passed
27.03 | Click on "My Apps".Click the "Personalise" icon. Verify personalize dialog slides up. Click the top right "X" button and verify dialog closes. | Passed
27.04 | Click on the user name in the banner after "Welcome". Verify personalize dialog slides down. Click the "Cancel" button. Verify dialog closes. | Passed
27.05 | Open the personalize dialog. Make changes in all of the tabs. Click "Save". Verify changes appear. Log out and log back in using the same user. Verify changes are still there. Open the personalize dialog and select default settings. Click "Save". Verify default settings appear. | Passed
28 | Annotations Logon using "sysadmin,syspwd", select Config "CscDemo", click "Multi-Media", enter "0" for policy and search. Find policy APV000009900 with description "Demo PDF". For that row, under Actions click on the "A" icon. Verify that the PDF opens with the annotation bar on the left. | Passed
28.01 | Highlight "NOTICE", click on the icon that appears, an edit dialog should appear, enter a comment and click "Save", verify that "NOTICE" is highlighted and the new note appears in the left bar. | Passed
28.02 | At the top of the left bar click the bubble icon, move the mouse over the document, verify the mouse cursor is a hand cursor, click anywhere in the document, an edit dialog should appear, enter a comment and click "Save", verify that a bubble box remains on the document and the new note appears in the left bar. | Passed
28.03 | Hover over the bubble box, a view dialog should appear, click the top right "pencil" icon, an edit dialog should appear, modify the text and click "Save", verify that the new text appears in the left bar and when you hover. | Passed
28.04 | Hover over the bubble box, a view dialog should appear, click the top right "reply" icon, enter some reply text, click "Save", verify the reply appears when you hover over the bubble box, verify the reply appears when you click the annotation in the left bar. | Passed
28.05 | Create another bubble annotation, hover over the new bubble box and click the top right "X" icon, in the delete confirm box click OK, verify it is deleted. | Passed
28.06 | Close the annotated document, on the "Demo PDF" row click the "A" icon again, verify the PDF opens with the annotation bar on the left, verify the added annotations appear in the left bar and on the document. | Passed
28.07 | Find policy APV000001500 with description "Demo Photo". For that row, under Actions click on the "A" icon. Verify that the photo opens with the annotation bar on the left. At the top of the left bar click the bubble icon and add a bubble annotation, verify it appears on the photo and in the left bar. | Passed
29 | Lucene Logon using "sysadmin,syspwd", select Config "CscDemo", click "Multi-Media", click the double arrow "Select Fields" icon, check the "File Contents" field, uncheck the "Date Added" and "Date Viewed" fields, click OK, verify the "File Contents" field appears in the search filter area. | Passed
29.01 | In the "File Contents" field box enter "BOXSTER", verify all other search fields are empty, click the "Search" icon, verify that two documents appear in the search results area, retrieve both documents and verify both contain the word "BOXSTER". | Passed
29.02 | Attach a text file containing the text "Another document with BOXSTER in it." Verify that it appears in the search results area. | Passed